## Blad1
Date | Priority | Module | Issue description | Reported by | Assigned to | Status
2015-01-20 | medium | DAQmx, function AddDAQmxChannel | When adding a DAQmx channel that is reserved, UI resources are added (channel & task tab) but the DAQmx task cannot be set up. The issue whether a resource is reserved or not should be either checked before adding UI or the UI added should be removed | Adrian
2015-01-20 | medium | DAQmx | Handle DAQmx errors when setting up DAQmx tasks and couple them to the task controller state. If an error is encountered while setting up a DAQmx task, then the task controller should be switched to an Unconfigured state so that it cannot be executed from the task tree | Adrian
2015-01-20 | low | DAQLab | When a task controller is dropped as a child of another task controller in the Task Tree, the selection jumps back to the first element in the Task Tree. This is because the task tree is re-assembled each time an a task controller item is dragged and dropped. This gives a slightly annoying user experience when assembing task trees. | Adrian
2015-06-13 | medium | Laser scanning and DAQmx interaction | When AI sampling rate is 200 KHz and 3x oversampling is used, so that an actual sampling rate of 600 KHz is used for a 5us pixel dwell time, then the image looks bad. For other values of the oversampling such as 1,2,4,5 the image looks good. Investigate why other values for the pixel dwell time such as 3.125 us give a bad image. Is the algorithm going wrong somewhere ?? | Adrian
2015-06-13 | low | data storage | If Rawdata default directory is not present, then create it by default. | Adrian
2015-07-20 | high | task controller | if task controller is set to iterate in parallel with child TCs then it receives an iteration event while it is in a done state. This error was seen before but it was corrected. It seems that it was corrected only for the case when the task controller is set to iterate before child TCs. In this case everything works fine. To reproduce the error, set up an UITC, add the scan engine as child and set it to iterate in parallel with child TCs. Add as children to the scan engine the DAQdev and pockells modules. Then set the UITC to do multiple iterations.